## 4WRS
Four-Week Rolling Schedule (4WRS) | [43 empty] | East Los Angeles College (ELAC)
Must be submitted to CPT PM at least 24 hours prior to the next meeting. | [43 empty] | Los Angeles City College (LACC)
[Enter General Contractor Name] |  | Campus: | [18 empty] | Prepared on: | [Enter date] | [19 empty] | C | Critical Path Activity | Los Angeles Harbor College (LAHC)
|  | Project Name: | [18 empty] | Prepared by: | [Enter Superintendent/PM/Scheduler Name] | [19 empty] | X | Non-Critical Activity | Los Angeles Mission College (LAMC)
[Insert GC company logo if desired. Erase this text to clear] |  | Project # | [18 empty] | Position/Title: | [20 empty] | P | Concrete Pour | Los Angeles Pierce College (LAPC)
|  | Contract #: |  |  |  | Task Order #: | [35 empty] | I | Inspection | Los Angeles Southwest College (LASC)
|  | DSA #: | [39 empty] | WD | Weather Delay | Los Angeles Trade Tech College (LATTC)
[42 empty] | H | Holiday | Los Angeles Valley College (LAVC)
[8 empty] | Schedule Period |  |  | from: |  |  | to: | [29 empty] | West Los Angeles College (WLAC)
[8 empty] | Previous Week (Actual Work Completed) | [6 empty] | Current Week | [6 empty] | Next Week | [6 empty] | 2 Weeks | [6 empty] | 3 Weeks | [6 empty] | Notes / Comments
Line | Activity Description (per latest schedule update) Critical Path Activity in Red | Activity I.D. (Per Schedule Update) | Trade | Subcontractor Name (if applicable) | Start Date | Finish Date | Duration (calendar days) | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun
Saturday | bar: Previous Week (Actual Work Completed) Sat to Previous Week (Actual Work Completed) Sun; Current Week Sat to Current Week Sun; Next Week Sat to Next Week Sun; 2 Weeks Sat to 2 Weeks Sun; 3 Weeks Sat to 3 Weeks Sun
A | B | C | D | Column2 | E | F | G | H | I | J | K | L | M | N | O | P | Q | R | S | T | U | V | W | X | Y | Z | AA | AB | AC | AD | AE | AF | AG | AH | AI | AC2 | AD3 | AE4 | AF5 | AG6 | AH7 | AI8 | Column1 | Duration (For Validation)
0 | [ENTER CATEGORY NAME]
1 | [Enter name of specific task/activity]
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16 | [ENTER CATEGORY NAME]
17 | [Enter name of specific task/activity]
18
19
20
21
22
23
24
25
26
27
28
29
30
Trades List | bar: Previous Week (Actual Work Completed) Mon to Current Week Tue
|  |  |  | Facility Construction Subgroup: | DIV 02 | - Existing Conditions
[5 empty] | DIV 03 | - Concrete
[5 empty] | DIV 04 | - Masonry
[5 empty] | DIV 05 | - Metals
[5 empty] | DIV 06 | - Wood, Plastics, and Composites
[5 empty] | DIV 07 | - Thermal and Moisture Protection
[5 empty] | DIV 08 | - Openings
[5 empty] | DIV 09 | - Finishes
[5 empty] | DIV 10 | - Specialties
[5 empty] | DIV 11 | - Equipment
[5 empty] | DIV 12 | - Furnishings
[5 empty] | DIV 13 | - Special Construction
[5 empty] | DIV 14 | - Conveying Equipment
|  |  |  | Facility Services Subgroup: | DIV 21 | - Fire Suppression
[5 empty] | DIV 22 | - Plumbing
[5 empty] | DIV 23 | - Heating, Ventilating, and Air Conditioning (HVAC)
[5 empty] | DIV 25 | - Integrated Automation
[5 empty] | DIV 26 | - Electrical
[5 empty] | DIV 27 | - Communications
[5 empty] | DIV 28 | - Electronic Safety and Security
|  |  |  | Site and Infrastructure Subgroup: | DIV 31 | - Earthwork
[5 empty] | DIV 32 | - Exterior Improvements
[5 empty] | DIV 33 | - Utilities
[5 empty] | DIV 34 | - Transportation
[5 empty] | DIV 35 | - Waterway and Marine Construction
|  |  |  | Process Equipment Subgroup: | DIV 40 | - Process Interconnections
[5 empty] | DIV 41 | - Material Processing and Handling Equipment
[5 empty] | DIV 42 | - Process Heating, Cooling, and Drying Equipment
[5 empty] | DIV 43 | - Process Gas and Liquid Handling, Purification & Storage Equipment
[5 empty] | DIV 44 | - Pollution and Waste Control Equipment
[5 empty] | DIV 45 | - Industry-Specific Manufacturing Equipment
[5 empty] | DIV 46 | - Water and Wastewater Equipment
[5 empty] | DIV 48 | - Electrical Power Generation
Note on D11: See Trades List below